## TEMPLATE KEY
KEY TO THIS TEMPLATE
1 | It's best to keep a clean TEMPLATE of this document so you always have one that hasn't been edited or tampered with
2 | Any instructions or examples will appear in light blue, please feel free to delete these.
3 | You can add Gridlines back into the document by going to View (above) and clicking on the 'Gridlines' checkbox
4 | The calls highlighted in YELLOW contain formulas and so be careful not to tamper with them otherwise they will stop automatically calculating the totals
FIND MORE FREE PROJECT MANAGEMENT TEMPLATES
1 | https://www.stakeholdermap.com/project-templates/project-management-templates.html
2 | https://clickup.com/blog/project-management-templates/
3 | https://www.hubspot.com/business-templates/project-management
PROJECT MANAGEMENT SOFTWARE
1 | Asana | https://asana.com/
2 | Clickup | https://clickup.com/
3 | Basecamp | https://basecamp.com/

## Project Timeline and Task list
[PROJECT TITLE] Project Delivery Timeline & Task List |  |  | Status Key
To Do
In Progress
Done
|  |  | Stuck |  |  |  |  | Gantt Chart
Cancelled
[8 empty] | March |  |  |  | April |  |  |  | Month |  |  |  | Month |  |  |  | Month |  |  |  | Month |  |  |  | Month |  |  |  | Month |  |  |  | Month |  |  |  | Month |  |  |  | Month |  |  |  | Month |  |  |  | Month
ACTIVITY/TASK | DESCRIPTION | OWNER | STATUS | TARGET START DATE | TARGET END DATE | ACTUAL DATE COMPLETED | NOTES | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
INSTRUCTIONS: Enter the name of the activity/task | Enter a description of the task to be completed | who is responsible for making this happen | You can click on the boxes below for a drop-down list | when does work on this need to start | when does this need to be completed by | when was the task actually completed | any additional notes to add
Event Content Schedule
Research content | Look into competitor workshops/organisations and identify key themes Explore evaluation and topics identified as relavant | Jay Stone | Done | 2023-03-12 | 2023-03-15 | 2023-03-13 | Delayed by one day due to bank holiday
Create skeleton schedule | Get a template for the schedule from online | Jay Stone | To Do | 2023-03-27 | 2023-03-28
Test V1 with test case | Identify 3 test case users Get an incentive to participate | Jay Stone | To Do | 2023-03-12 | 2023-04-05
Venue/Hosting
Research potential venues to partner with | Start to network with potential venues Contact Beldi Maison to see if they are interested | Jay Stone | Done | 2023-03-27 | 2023-04-05 | 2023-04-05
Arrange catering/set up/logistics with venue | Just cookies and soft drinks - try to arrange for them to pay | Jay Stone | To Do | 2023-04-05 | 2023-04-05
Create a running order | Get a running order template from internet Create a running order and agree with venue | Jay Stone | To Do | 2023-04-26 | 2023-04-26
[INPUT TASK GROUP NAME]
[INPUT TASKS] | - ... - … - …
[INPUT TASKS] | - ... - … - …
[INPUT TASKS] | - ... - … - …
[INPUT TASK GROUP NAME]
[INPUT TASKS] | - ... - … - …
[INPUT TASKS] | - ... - … - …
[INPUT TASKS] | - ... - … - …
[INPUT TASK GROUP NAME]
[INPUT TASKS] | - ... - … - …
[INPUT TASKS] | - ... - … - …
[INPUT TASKS] | - ... - … - …
[INPUT TASK GROUP NAME]
[INPUT TASKS] | - ... - … - …
[INPUT TASKS] | - ... - … - …
[INPUT TASKS] | - ... - … - …
[INPUT TASK GROUP NAME]
[INPUT TASKS] | - ... - … - …
[INPUT TASKS] | - ... - … - …
[INPUT TASKS] | - ... - … - …

## SWOT
[PROJECT NAME] SWOT ANALYSIS
SWOT stands for Strengths, Weaknesses, Opportunties and Threats
It is a tool that is useful for assessing a project before you begin or throughout to bring awareness to how to optimise strengths and opportunities to your advantage, and minimise or mitigate weaknesses and threats as much as possible.
Once you've identified your Strengths, Weaknesses, Opportunties and Threats, consider for each point how you can optimise or take advantage of strengths and opportunities, and how you can minimise or mitigate weaknesses and threats
| Department name: | Created date:
| Prepared by: | Review date:
| STRENGTHS What strengths do you have that will help you deliver this successfully? What skills, resources, contacts do you already have? | WEAKNESSES What are your areas of improvement that you will need to consider to be successful? What are the gaps? How can you fill these gaps?
| e.g. Jay's knowledge and existing content Venue's email marketing database and socials | e.g. No funding Pilot event - no word of mouth or evidence to use of value yet
| OPPORTUNITIES What opportunities could you explore and exploit? What is the vision and potential of this? | THREATS What are your biggest challenges? What are your constraints? What are the potential risks that you will need to consider? e.g. safeguarding What could get in the way of your success? In what ways can you mitigate or minimise each risk? i.e. insurance, safeguarding plan
| e.g. Potential to attain government funding and run these workshops for free for participants Potential to tap into NCT network | e.g. Other local organisations or workshops delivering the same thing Lack of funding and support means we don't get the traction needed

## Stakeholder Analysis
[PROJECT NAME] Stakeholder Identification |  |  | Stakeholder Matrix |  |  |  | Stakeholder Empathy Mapping
| Identify all the stakeholders in your project. |  | Identify all the stakeholders in your project. Plot them on the matrix in terms of their influence over the project and their interest in the project. You can then identify what kind of action you should take with them through a communication plan. Plan the different strategies you're going to use with each group. |  |  |  |  | Using an empathy map can be useful to help you think about issues from the perspective of your stakeholders. The below template can be mapped out to think about what might be influencing your stakeholders thoughts. Try completing the below empathy map from the perspective of some of your recent stakeholders. Write who they are in the middle of the map and answer the questions around the edge to reflect on what their view points might be.
|  | Jay - organiser Participants Venue Potential future participants Potential future funders Other potential local venues |  |  | Stakeholder Matrix
|  |  | Influence/Power of Stakeholder | Low High |  |  |  | l | What do they think and feel?
[8 empty] | l | What really counts?
[8 empty] | l | What are their major preoccupations?
[8 empty] | l | What are their worries?
[8 empty] | l | What are their aspirations?
[8 empty] | l | What do they want or need?
[8 empty] | l | How do they measure success?
[8 empty] | l | What do they see
[8 empty] | l | What is their environment?
[8 empty] | l | Who are their peers?
[8 empty] | l | Who are their colleagues?
Low High
[5 empty] | Interest of Stakeholder |  |  | l | What do they hear?
[8 empty] | l | What do peers/colleagues say to them?
[5 empty] | Stakeholder Matrix |  |  | l | What would their boss say to them?
[8 empty] | l | Who else might influence them?
|  |  | Influence/Power of Stakeholder | Low High
[5 empty] | Venue | Participants
[5 empty] | Potential future participants |  |  | l | What do they do?
[5 empty] | Potential future funders |  |  | l | What is their public attitude?
[8 empty] | l | How do they present themselves?
[8 empty] | l | How do they behave towards others?
Other potential venues
Low High
Interest of Stakeholder
High influence, less interested: Provide sufficient information to these stakeholders to ensure that they are up to date but not overwhelmed with data.
Keep satisfied
High influence, highly interested: These are the stakeholders you must engage and make the greatest efforts with.
Manage closely
Low influence, less interested: Provide these stakeholders with minimal communication.
Monitor (Minimum effort)
Low influence, highly interested:
Keep these stakeholders adequately informed, talk to them to ensure that no major issues arise.
Keep informed

## Communication Plan
[PROJECT NAME] Project Communication Plan
One of the biggest risks you have on a project is actually it’s stakeholders. The most likely reason a stakeholder may object to the project is that they have misunderstood what the project is trying to achieve, and more often than not it's due to ineffctive communication. Once you've identified your stakeholder and their relataive interest and influence on the project, now it's time to communicate, communicate, communicate.
| Method | Receiver | Sender | Message | When
| e.g. Insta story (tagging Bromley as location) - tagging venue and Jaystonechanges accounts | potential participants, Jays social media follows, venues social media followers | Jay | - who the workshop is for -what it will cover - benefits - how to sign up | e.g. 1 insta story per week
| e.g. Email | Signed up participants | Jay | - preparation email ahead of event - event time/date and location - how to log in to find ticket and directions - what to do on arrival | e.g. 2 days before the workshop

## Roles & Responsbilities
[PROJECT TITLE] Roles & Responsibilities |  |  | Status Key
Name | Role/Title | Responsibilities/Tasks | Email | Telephone
e.g. Ngozi Bhatt | Marketing Manger - from Agency | - creating a marketing plan - updating social media after an event - creating copy for marketing material | nbhatt@email.com | 07908701923
- ... - … - …
- ... - … - …
- ... - … - …
- ... - … - …
- ... - … - …
- ... - … - …
- ... - … - …
- ... - … - …
- ... - … - …
- ... - … - …
- ... - … - …
- ... - … - …
- ... - … - …
- ... - … - …
- ... - … - …

## Lessons Learnt Log
[PROJECT TITLE] Lessons Learnt Log
Documented experiences that can be used to improve the future management of projects, programmes and portfolios
# | Lesson Detail | What does it effect? | Who does it effect? | Recommendation | Additional notes | Date logged | Logged by (initials)
1 | e.g. Social media posts need to be shorter - they are too long | Lack of engagement in posts | Brand of business engagement & attendance | Limit social posts to max 300 words | Consider researching optimal word count for different social media platforms - do some research on optimal word count | 2023-03-12 | Jay Stone
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## Risk Register
[PROJECT NAME] Risk Register |  |  |  |  | Key
Risk is the potential of a situation or event happenign that will impact your project. It's an uncertain event that if it occurs will have an effect on the project - it is not a known thing. Whilst the very definition of risk suggests uncertainty, generally, there are still things that can be done to: 1. affect whether a risk occurs or not and/or 2. influence how much of an impact it might have on a project if it occurs. |  |  |  |  | High 9+
Medium 4-8
Low 1-3
| Risk Description | Effect | Probability | Impact | Current Rating | Response | Owner
| Risk Cause/Event | Impact/Consequences | (1 = Unlikely / 2 = Possible/ 3 = Likely) | (1 = Low / 2 = Medium/ 3 = High) | Probability x Impact = Rating Use the drop-down list below | Minimisation/Mitigation Measures | Who is best placed to deal with the risk?
| e.g. Poor communications and marketing copy via social media | Lack of engagement, interest and attendance | 2 | 2 | Medium 4-8 | Engage with a social media agency who have worked on similar events with success | Jay Stone

## Risk Classification
[PROJECT NAME] Risk Classification Matrix
| PROBABILITY | Likely | 3 | Low | MEDIUM | High
|  | Possible | 2 | Low | MEDIUM | MEDIUM
|  | Unlikely | 1 | Low | Low | Low
|  |  |  | 1 | 2 | 3
|  |  |  | Low | Medium | High
IMPACT
Rating Key
|  | Key | Prob | Impact | Severity (Impact * Prob) | Rating
|  |  | 1 | 1 | 1 | LOW
|  | High | 1 | 2 | 2 | LOW
|  | Medium | 1 | 3 | 3 | LOW
|  | Low | 2 | 1 | 2 | LOW
|  |  | 2 | 2 | 4 | MEDIUM
|  |  | 2 | 3 | 6 | MEDIUM
|  |  | 3 | 1 | 3 | MEDIUM
|  |  | 3 | 2 | 6 | MEDIUM
|  |  | 3 | 3 | 9 | High

## Budget Forecast
[PROJECT TITLE] Basic Budget Forecast
The calls highlighted in YELLOW contain formulas and so be careful not to tamper with them otherwise they will stop automatically calaculating the totals
| Title | Forecast | Actual | Title | Forecast | Actual
| Direct Costs |  |  | Direct Costs
| Venue Room Charges | 300 | 0
| Energy | 50 | 0
| Furniture Hire Costs | 100 | 0
| Worksheets printing | 10 | 15
| Local advertising | 30 | 15
| Catering | 10 | 8.25
| Total Costs | 500 | 38.25 | Total Costs | 0 | 0
| Revenue |  |  | Revenue
| Ticket Sales | 100 | 50
| Funding | 0 | 0
| Total Revenue | 100 | 50 | Total Revenue | 0 | 0
| Gross Margin |  |  | Gross Margin
| TOTAL | -400 | 11.75 | TOTAL | 0 | 0